## Project Timeline
BEYOND THE BENCH: LAW, JUSTICE, AND COMMUNITIES SUMMIT
Event Timeline 12/14/2016
PROJECT DETAILS
| DATE | MILESTONE | POSITION | BASELINE
| 2016-09-15 | Project Start | 10 | 1
| 2016-09-22 | Research and Secure Venue | -10 | 1
| 2016-10-14 | Save the Date Sent | 10 | 1
10 | 2016-10-21 | Secure Presenters | -10 | 1
| 2016-11-03 | Confirm Security | 10 | 1
| 2016-11-17 | RSVP Date | -10 | 1
| 2016-12-01 | Op-Ed Sent | 10 | 1
| 2016-12-14 | Event Date | -10 | 1
| 2016-12-15 | Thank Yous | 10 | 1